## Tasks
RSC Bot
[6 empty] | January | [18 empty] | Februrary | [19 empty] | March | [20 empty] | April
[6 empty] | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12
| TASK NAME | START DATE | END DATE | DURATION (HOUR) | TEAM MEMBER | January 7: WEEK 1; January 14: WEEK 2; January 21: WEEK 3; January 28: WEEK 4; Februrary 4: WEEK 5; Februrary 11: WEEK 6; Februrary 18: WEEK 7; Februrary 25: WEEK 8; March 4: WEEK 9; March 11: WEEK 10; March 18: WEEK 11; March 25: WEEK 12; April 1: WEEK 13; April 8: WEEK 14 | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 |  |  |  |  | WEEK 23 |  |  |  |  | WEEK 24 |  |  |  |  | WEEK 25 |  |  |  |  | WEEK 26
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Coding
| Motor Interfacing | 2019-03-11 |  |  | Chikere | bar: WEEK 9 M to WEEK 10 F
| Ultrasound Interfacing | 2019-02-04 |  | 5 | River | bar: WEEK 5 M to WEEK 6 F
| Basic Path Following Code | 2019-01-21 |  | 20 | River | bar: WEEK 3 M to WEEK 4 F; WEEK 6 M to WEEK 7 F
| System Calibration | 2019-02-25 |  |  | River | bar: WEEK 8 M to WEEK 9 F
| PID Interfacing | 2019-02-25 |  |  | Skyler | bar: WEEK 8 M to WEEK 9 F
| Basic PID Model | 2019-02-04 |  | 3 | Skyler | bar: WEEK 5 M to WEEK 6 F
| Bluetooth Interfacing | 2019-02-07 |  | 15 | River | bar: WEEK 5 M to WEEK 7 F
| General Debugging | 2019-03-18 |  |  | River | bar: WEEK 10 M to WEEK 11 F
| Full Path Following Code |  |  |  | River | bar: WEEK 10 M to WEEK 11 F
| Full PID Integration |  |  |  | Skyler | bar: WEEK 10 M to WEEK 11 F
Design
| Torque | 2019-01-28 |  | 4 | Chikere | bar: WEEK 4 M to WEEK 6 F
| System Integration | 2019-03-11 | bar: WEEK 9 M to WEEK 10 F
| Proposal | 2019-01-07 | 2019-01-13 | 10 | River | bar: WEEK 1 M to WEEK 1 F
Skyler | bar: WEEK 1 M to WEEK 1 F
Chikere | bar: WEEK 1 M to WEEK 1 F
| Dimensions | 2019-01-28 | 2019-02-10 | 2 | River | bar: WEEK 4 M to WEEK 6 F
Chikere | bar: WEEK 4 M to WEEK 6 F
Skyler | bar: WEEK 4 M to WEEK 6 F
| Chassis Model (CAD) | 2019-02-25 |  |  | Chikere | bar: WEEK 8 M to WEEK 10 F
| Circuit Schematic | 2019-02-25 |  |  | Skyler | bar: WEEK 8 M to WEEK 10 F
| Decide Chassis Material | 2019-02-04 |  |  | Skyler | bar: WEEK 5 M to WEEK 9 F
Chikere | bar: WEEK 5 M to WEEK 9 F
River | bar: WEEK 5 M to WEEK 9 F
| Power Consumption | 2019-01-28 | 2019-02-10 |  | Chikere | bar: WEEK 4 M to WEEK 6 F
| Build Chassis | 2019-03-18 | bar: WEEK 10 M to WEEK 11 F
| Prep for Design Review | 2019-03-25 |  |  | Chikere | bar: WEEK 11 M to WEEK 13 F
River | bar: WEEK 11 M to WEEK 13 F
Skyler | bar: WEEK 11 M to WEEK 13 F
| Project Plan | 2019-02-04 | 2019-02-10 | 5 | Chikere | bar: WEEK 5 M to WEEK 6 F
Skyler | bar: WEEK 5 M to WEEK 6 F
River | bar: WEEK 5 M to WEEK 6 F
| Preliminary Design Review | 2019-04-15 |  |  | Skyler | bar: WEEK 14 M to WEEK 14 F
Chikere | bar: WEEK 14 M to WEEK 14 F
River | bar: WEEK 14 M to WEEK 14 F
| Desired Speed | 2019-02-04 | 2019-02-17 | 1 | Chikere | bar: WEEK 5 M to WEEK 6 F
| Poster Desing/Build |  |  |  | Chikere
Skyler
River
| Final Schematic Design |  |  |  | Chikere
Skyler
River
| Final Design Review |  |  |  | Chikere
Skyler
River
Resources & Funding
| Office Of Undergraduate Research | 2019-03-11 |  |  | Chikere | bar: WEEK 9 M to WEEK 12 F
Skyler | bar: WEEK 9 M to WEEK 12 F
River | bar: WEEK 9 M to WEEK 12 F
| Meet with Chassis Advisor | 2019-01-28 |  | 3 | Chikere
Skyler
River
| Cost Analysis | 2019-01-14 | 2019-01-27 | 1 | Skyler | bar: WEEK 2 M to WEEK 3 F
River | bar: WEEK 2 M to WEEK 3 F
Chikere | bar: WEEK 2 M to WEEK 3 F
| Wildcat Seed Fund | 2019-03-29 |  |  | Chikere | bar: WEEK 13 F
Skyler | bar: WEEK 13 F
River | bar: WEEK 13 F
Parts
| Tentative Part List | 2019-01-14 | 2019-01-20 | 1 | Chikere
Skyler
River
| Identify and Order Test Parts | 2019-01-21 | 2019-01-27 | 1 | River | bar: WEEK 3 M to WEEK 3 F
Chikere | bar: WEEK 3 M to WEEK 3 F
| Identify and Order Test Chassis | 2019-01-21 | 2019-01-27 | 1 | River | bar: WEEK 3 M to WEEK 3 F
Skyler | bar: WEEK 3 M to WEEK 3 F
| Order 2nd Round of Test Parts | 2019-01-28 | 2019-02-03 | 1 | River
| Order Final Round of Parts | 2019-02-11 |  |  | Chikere
Research
| Motor Research | 2019-01-21 |  | 20 | Chikere | bar: WEEK 3 M to WEEK 5 F
| PID Research | 2019-01-14 |  | 30 | Skyler | bar: WEEK 2 M to WEEK 4 F
| Sensor Research | 2019-01-14 | 2019-01-27 | 3 | Chikere | bar: WEEK 2 M to WEEK 3 F
| Chassis Research | 2019-02-11 |  | 5 | Chikere
| Microcontroller Research | 2019-01-14 | 2019-01-20 | 1 | River
| Wheel Research | 2019-02-04 |  | 3 | Chikere | bar: WEEK 5 M to WEEK 6 F
| Resource Research | 2019-01-14 | 2019-01-20 | 5 | Chikere
Skyler
River
| Battery Research | 2019-02-04 |  | 1 | Chikere | bar: WEEK 5 M to WEEK 6 F

## Budget
RSC BOT
Part | Cost | Source
Arduino Mega | 40 | https://www.amazon.com/ARDUINO-MEGA-2560-REV3-A000067/dp/B0046AMGW0/ref=sr_1_3?keywords=arduino+mega&qid=1550116054&s=gateway&sr=8-3
Motor Drivers | 20 | https://www.robotshop.com/en/cytron-10a-5-30v-dual-channel-dc-motor-driver.html
Ultrasound | 5
IR Sensor Array x2 | 30 | https://www.pololu.com/product/961
Battery | 100
Motor (x2) | 100
Chassis | 50
PCB | 25
3D Printed Parts | 30
Bluetooth Module | 15
MISC | 100
Total: | 515